Name of Museum

Exhibition Title

Timeline

| Editorial | Design | Proofing | Print |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Edited/proofed copy & images supplied | Fri 6th Dec |
|  |  |  |  | Design Start | Mon 9th Dec |
|  |  |  |  | First set of lasers to client | Wed 18th Dec |
|  |  |  |  | First corrections start | Thu 19th Dec |
|  |  |  |  | Final set of lasers to client for signoff | Thu 2nd Jan |
|  |  |  |  | Laser proof signoff | Thu 2nd Jan |
|  |  |  |  | Design end | Fri 3rd Jan |
|  |  |  |  | Proofing start | Mon 6th Jan |
|  |  |  |  | Proofing end | Tue 7th Jan |
|  |  |  |  | Digital proof to client for approval | Wed 8th Jan |
|  |  |  |  | Digital proof signoff | Wed 8th Jan |
|  |  |  |  | To print | Thu 9th Jan |
|  |  |  |  | Delivery | Tue 14th Jan |